## Gantt Chart Template
ECE 597/697SD: Team 8 Gantt Chart | [10 empty] | https://goo.gl/PXLbMe
Alex
John
| PROJECT TITLE | Deep-Learning Based Sensor Fusion for MR Systems |  |  |  | PROJECT NUMBER |  | 8 |  |  |  |  | Zach
| TEAM ADVISOR | Fatima Anwar |  |  |  | PROJECT DUE DATE |  | 2021-12-06 |  |  |  |  | Zhehang
| TASK TITLE | PRIMARY TASK OWNERS | START DATE | DUE DATE | Week 1 |  | Week 2 |  | Week 3 | Week 4 |  | Week 5 |  | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
[5 empty] | 30 Sept. - 3 Oct. |  | 4 Oct - 10 Oct. |  | 11 Oct. 17 Oct. | 18 Oct. - 24 Oct. |  | 25 Oct. - 31 Oct. |  | 1 Nov. - 7 Nov. | 8 Nov. - 14 Nov. | 15 Nov. - 21 Nov. | 21 Nov. - Nov. 28 | Nov. 29 - Dec. 6
Extracting Hololens Inertial Data
| Headset Acquisition & Setup | John/Zach
| Unity Engine Setup/Headset Pairing | John/Zach
| Acquire Dataset(s) from Hololens | John/Zach
Deep-Learning SF Research
| Research SImilar SF Models | Alex/Zhehang
| Build DNN Model Structure | Alex/Zhehang
| Obtain Relevant Formatted Training Dataset(s) | Alex/Zhehang
| Train DNN Model | Alex/Zhehang
Sensor Fusion Model Testing/Evaluation
| Develop SF Algorithm Prototype in Python | Alex/Zhehang
| Analyze Performance of/Debug Prototype | Alex/Zhehang
| Finalize Algorithm and Input DNN Dataset | Alex/Zhehang
| Evaluate Accuracy of Algorithm with Expected Results | John/Zach
| Create Graphical/Figure Representation of Algorithm Results | John/Zach
Accuracy Analysis of SF Algorithm
| Format/Import SF Model Results to MATLAB | All Members
| Develop/Produce Accuracy Test in MATLAB | All Members